## 🏠 Dashboard
🛕 Ultimate Travel Buddy — Product OS
Product | Ultimate Travel Buddy | 📊 Status Summary
Version | v1.0 — Play Store MVP
Vision | The app that travels with you
USP | One place for everything related to your trip | ✅ Done | 12
Current Phase | Foundation → v1.0 Launch | 🔵 In Progress | 5
Launch Goal | Polished Play Store release | 📋 Todo | 20
|  | 🔴 Critical | 4
|  | 💭 Backlog | 15
⭐ Golden Questions — Ask before every feature
1. Does this reduce the number of apps opened during travel?
2. Does this reduce manual input?
3. Does this create a memorable travel experience?

## 🚀 v1.0 Launch Gap
🚀 v1.0 Launch Gap — What needs to be done before Play Store
Priority | Category | Item | Status | Notes | Done?
🔴 Critical | CRUD | Edit Activity in Itinerary | Done | Long press → Edit modal | ✅
🔴 Critical | CRUD | Delete Activity in Itinerary | Done | Long press → Delete | ✅
🔴 Critical | CRUD | Delete Accommodation | Done | Long press → Delete + cascade | ✅
🔴 Critical | CRUD | Edit Accommodation | Done | Long press → Edit form | ✅
🔴 Critical | CRUD | Edit Transport | Done | Long press → Edit modal | ✅
🔴 Critical | CRUD | Edit/Delete Expense | Done | Long press → Edit/Delete | ✅
🔴 Critical | CRUD | Destinations CRUD in Trip Settings | Done | Add/Delete destinations | ✅
🔴 Critical | Permissions | Owner/Editor role system | Done | useTripPermissions hook | ✅
🔴 Critical | Permissions | Invite with role selector (Owner/Editor) | Done | trip_invitations table | ✅
🔴 Critical | Permissions | Editors cannot delete trip | Done | Blocked in TripSettings | ✅
🔴 Critical | Notifications | Replace mock notifications with real data | Done | Generated from DB | ✅
🔴 Critical | Itinerary | Complete Itinerary redesign | Done | Trip selector, calendar, Day X of Y | ✅
🟡 High | UI | My Trips screen audit | Done | ~90% complete, archive future | ✅
🟡 High | UI | Trip Overview screen audit | Done | ~95% complete | ✅
🟡 High | UI | Overal design | Done | inconsistent UI, too basic dialog windows, icons need replacing with custom icons, fix home screen layout, check background colors
🟡 High | UI | Memories/Recap screen audit | Done | ~90%, Travel Book done | ✅
🟡 High | UI | Packing screen audit | Done | ~70%, acceptable for v1.0 | ✅
🟡 High | Edge-to-edge | All screens edge-to-edge | Done | statusBarHeight applied | ✅
🟡 High | Realtime | Realtime sync per screen | Done | useRealtimeSync hook | ✅
📋 Play Store | Legal | Privacy Policy URL | Todo | Need public URL | ⬜
📋 Play Store | Account | Google Play Developer Account | Todo | Create & verify ($25) | ⬜
📋 Play Store | Build | Android App Bundle (AAB) | Todo | EAS Build setup | ⬜
📋 Play Store | Assets | Store listing assets | Todo | Screenshots, icon, description | ⬜
📋 Play Store | Testing | Closed testing plan | Todo | Internal testing first | ⬜

## ✅ CRUD Audit
✅ CRUD Audit — Create / Read / Edit / Delete per module
Module | Create | Read | Edit | Delete | Notes
Activities | ✅ | ✅ | ✅ Long press | ✅ Long press | Edit/Delete via long press → Alert
Transport | ✅ | ✅ | ✅ Long press | ✅ Long press | EditTransportForm in BottomSheet
Accommodation | ✅ | ✅ | ✅ Long press | ✅ Long press | Cascade delete activities + docs
Expenses | ✅ | ✅ | ✅ Long press | ✅ Long press | Edit reuses AddExpenseModal
Documents | ✅ | ✅ | ❌ Missing | ✅ | Edit not implemented yet
Packing | ✅ | ✅ | ❌ Missing | ✅ | Edit not implemented yet
Destinations | ✅ | ✅ | ❌ Missing | ✅ | In Trip Settings
Journal | ✅ | ✅ | ✅ | ✅ | Full CRUD complete
Trips | ✅ | ✅ | ✅ | ✅ | Full CRUD in Trip Settings
Trip Members | ✅ | ✅ | ✅ Role change | ✅ Remove | Owner can promote/remove

## 🗺️ Roadmap
🗺️ Roadmap — Phases & Status
Phase | Version | Epic | Status | Key Deliverables | Notes
Phase 0 | v1.0 | Clean v1 Foundation | Done | Remove dead UI, real data, edge-to-edge | Completed ✅
Phase 1 | v1.0 | Trip Context Layer | Done | TripContext lightweight, currentUserId, helpers | Completed ✅
Phase 2 | v1.0 | Travel Group | Done | Invite by code, Owner/Editor roles, trip_invitations | Completed ✅
Phase 3 | v1.0 | Itinerary Upgrade | Done | Auto-create from Transport/Accommodation | Completed ✅
Phase 4 | v1.0 | Real Data Everywhere | Done | Weather, hero emoji, real stats | Completed ✅
Phase 5 | v1.0 | Budget Finance Hub | Done | Split, settlement, multi-currency | Completed ✅
Phase 6 | v1.0 | Journal + Travel Book | Done | Memory of Day, photo gallery, Travel Book PDF | Completed ✅
Phase 7 | v1.0 | Transport & Accom Integration | Done | Auto-docs, budget prompt, map pins | Completed ✅
Phase 8 | v1.0 | Explore/Map Upgrade | Done | Today's Plan, filters, saved places, ExploreItem model | Completed ✅
CRUD Audit | v1.0 | Complete CRUD Everywhere | Done | Edit/Delete for all modules | Completed ✅
Permissions | v1.0 | Travel Group Roles | Done | Owner/Editor permissions enforced | Completed ✅
Notifications | v1.0 | Real Notifications | Done | Generated from DB, context-aware | Completed ✅
Play Store Prep | v1.0 | Launch Readiness | Todo | Privacy policy, AAB, store listing | In progress 🔵
Phase 9 | v1.1 | Smart Import (Premium) | Backlog | PDF, Flight, Booking, Airbnb, Gmail | Premium feature
Phase 10 | v1.1 | Premium Layer | Backlog | Monetization, subscription, unlock gates | Post-launch
Travel Book AI | v2.0 | AI Story + Themes | Backlog | AI-generated travel story, multiple themes | Future

## ⚡ Features
⚡ Feature Tracker
Module | Feature | Type | Status | Version | Notes
Home | Dynamic greeting (time-aware) | Free | Done | v1.0 | Good morning/afternoon/evening
Home | Context card (priority-based) | Free | Done | v1.0 | Flight/checkin/budget/journal
Home | Weather for destination | Free | Done | v1.0 | WeatherAPI.com
Home | Hero emoji per destination | Free | Done | v1.0 | destinationHero.ts mapping
Home | Travel Feed structure | Free | Todo | v1.1 | Framework ready, needs population
Itinerary | Trip selector | Free | Done | v1.0
Itinerary | Day X of Y navigation | Free | Done | v1.0
Itinerary | Calendar jump modal | Free | Done | v1.0
Itinerary | Auto-create from Transport | Free | Done | v1.0 | source_id + source_type linking
Itinerary | Auto-create from Accommodation | Free | Done | v1.0 | Check-in/out events
Budget | Split expenses | Free | Done | v1.0 | split_with JSONB
Budget | Settlement summary | Free | Done | v1.0 | Who owes whom
Budget | Multi-currency | Free | Done | v1.0 | frankfurter.app exchange rates
Budget | Category breakdown | Free | Done | v1.0
Journal | Memory of the Day | Free | Done | v1.0 | 1 year ago banner
Journal | Photo gallery tab | Free | Done | v1.0
Journal | AI daily summary | Free | Done | v1.0 | Claude Sonnet via API
Travel Book | PDF export | Premium | Done | v1.0 | expo-print, modular sections
Explore | Today's Plan section | Free | Done | v1.0
Explore | Filters (Food/Hotels/Transport) | Free | Done | v1.0
Explore | Saved places | Free | Done | v1.0 | saved_places table
Explore | ExploreItem model (extensible) | Free | Done | v1.0 | Future-proof for mixing sources
Travel Group | Invite by code | Free | Done | v1.0 | trip_invitations table
Travel Group | Owner/Editor roles | Free | Done | v1.0 | useTripPermissions hook
Travel Group | Real-time sync | Free | Done | v1.0 | useRealtimeSync per screen
Import | PDF Import | Premium | Backlog | v1.1
Import | Flight Import | Premium | Backlog | v1.1
Import | Booking.com Import | Premium | Backlog | v1.1
Import | Airbnb Import | Premium | Backlog | v1.1
Import | Gmail/Email parsing | Premium | Backlog | v2.0
AI | AI Trip Story | Premium | Backlog | v2.0
AI | AI Itinerary Optimization | Premium | Backlog | v2.0

## 🧪 QA Checklist
🧪 QA Checklist — Before Play Store Launch
Area | Check | Status | Notes | Tested By
Auth | App installs cleanly on fresh Android | Todo
Auth | Login/register works on fresh install | Todo
Auth | Logout clears all state | Todo
Trips | Create trip works end-to-end | Todo
Trips | Join trip by code works | Todo
Trips | Delete trip removes all related data | Todo
Trips | Trip owner can invite with role | Todo
Trips | Editor cannot delete trip | Todo
Itinerary | Add activity appears in list | Todo
Itinerary | Edit activity saves correctly | Todo
Itinerary | Delete activity removes from list | Todo
Itinerary | Transport auto-creates itinerary item | Todo
Itinerary | Accommodation creates check-in/out items | Todo
Budget | Add expense appears in timeline | Todo
Budget | Edit expense updates correctly | Todo
Budget | Delete expense removes from list | Todo
Budget | Settlement calculates correctly | Todo
Budget | Multi-currency conversion works | Todo
Journal | Add entry saves with photos | Todo
Journal | Edit entry updates correctly | Todo
Journal | AI summary generates | Todo
Journal | Travel Book PDF exports | Todo
Explore | Today's Plan shows correct activities | Todo
Explore | Save/unsave places works | Todo
Transport | Add flight creates document + activity | Todo
Transport | Delete transport removes linked items | Todo
Accommodation | Add hotel creates check-in doc + events | Todo
Accommodation | Delete removes linked activities + docs | Todo
Realtime | Raul adds expense → Vlad sees it instantly | Todo
Realtime | Raul adds activity → Vlad sees it instantly | Todo
UI | No hardcoded demo data visible | Todo
UI | No inactive buttons visible | Todo
UI | Edge-to-edge works on all screens | Todo
Play Store | Privacy policy URL works | Todo | Need URL
Play Store | Data Safety answers prepared | Todo
Play Store | AAB builds without errors | Todo
Play Store | Internal testing track setup | Todo

## 🐛 Bugs
🐛 Bug Tracker
Priority | Module | Bug | Repro Steps | Status | Fixed In
— | — | No bugs reported yet 🎉

## 💰 Monetization
💰 Monetization Strategy
✅ Free Features | ⭐ Premium Features
✅ Manual trip creation | ⭐ Automatic flight import
✅ Itinerary (full) | ⭐ Booking.com import
✅ Budget basic | ⭐ Airbnb import
✅ Journal basic | ⭐ Gmail/email parsing
✅ Accommodation | ⭐ PDF parsing
✅ Transport | ⭐ AI itinerary optimization
✅ Documents | ⭐ AI journal/travel story
✅ Packing | ⭐ Travel Book themes
✅ Explore/Map basic | ⭐ Unlimited trips
✅ Profile/Settings | ⭐ Large travel groups (5+)
✅ Small travel group (2 members) | ⭐ Expense settlement (advanced)
✅ Real-time sync | ⭐ Advanced offline mode
✅ Travel Book PDF (basic) | ⭐ Smart reminders
⭐ Travel Inbox
💡 Positioning: 'Premium saves time before and during every trip' — not 'Pay to use the app'

## 🗄️ Database
🗄️ Database Schema — Key Tables
Table | Key Columns | RLS | Realtime | Notes
trips | id, name, start_date, end_date, budget, currency, status, cover_destination, invite_code, created_by | ✅ | ❌ | Legacy invite_code kept for fallback
trip_members | trip_id, user_id, role (owner/editor) | ✅ | ❌
trip_invitations | trip_id, invite_code, role, created_by, max_uses, uses, expires_at | ✅ | ❌ | New role-based invite system
destinations | trip_id, name, country, nights, order_index | ✅ | ❌
activities | trip_id, title, category, date, time, location, status, source_id, source_type, source_event_type | ✅ | ✅ | source_* for auto-created items
transport | trip_id, type, airline, flight_number, departure_location, arrival_location, departure_time, arrival_time | ✅ | ✅
accommodations | trip_id, name, address, check_in, check_out, platform, price, booking_reference | ✅ | ✅
expenses | trip_id, title, amount, currency, category, date, paid_by, split_with (jsonb), local_amount, local_currency | ✅ | ✅ | split_with for group expenses
documents | trip_id, user_id, title, type, expires_at, file_url, source_id, source_type | ✅ | ❌ | source_* for auto-created docs
journal_entries | trip_id, title, content, mood, highlight, favorite_meal, location, photos (jsonb), date | ✅ | ✅
packing_items | trip_id, name, category, packed, assigned_to | ✅ | ❌
saved_places | trip_id, user_id, item_id, item_type, title, emoji, location | ✅ | ❌ | For Explore saved places
profiles | id, name, email, default_currency, language, travel_style, flight_seat, emergency_contact_name/phone, frequent_flyer (jsonb) | ✅ | ❌

## 🏪 Play Store
🏪 Play Store Launch Checklist
Category | Task | Status | Notes
Account | Create Google Play Developer Account ($25 one-time) | Todo | play.google.com/console
Account | Verify identity & payment | Todo | Can take 48h
Legal | Create Privacy Policy page | Todo | Use a free generator or write custom
Legal | Host Privacy Policy at public URL | Todo | GitHub Pages or simple website
Legal | Complete Data Safety questionnaire | Todo | Declare data collection/sharing
Build | Configure EAS Build (eas.json) | Todo | expo.dev EAS account needed
Build | Generate production Android App Bundle (.aab) | Todo | eas build --platform android
Build | Test AAB on physical device | Todo
Assets | App icon (512x512 PNG) | Todo | No transparency
Assets | Feature graphic (1024x500 PNG) | Todo | Banner shown in store
Assets | Screenshots (min 2, max 8) | Todo | Phone screenshots required
Assets | Short description (80 chars max) | Todo
Assets | Full description (4000 chars max) | Todo
Testing | Set up internal testing track | Todo | Add testers by email
Testing | Upload AAB to internal testing | Todo
Testing | Test all critical flows on fresh install | Todo | See QA Checklist tab
Testing | Collect feedback from internal testers | Todo
Launch | Set up closed testing (optional) | Todo | Invite external testers
Launch | Submit for review | Todo | Can take 3-7 days
Launch | Monitor crashes in Play Console | Todo | After launch

## 💭 Future Backlog
💭 Future Backlog — Post v1.0 Ideas
Area | Idea | Impact | Target | Notes
Home | Travel Feed (activity stream) | High | v1.1 | Alex added photos, Raul added expense
Home | Weather forecast (multi-day) | Medium | v1.1 | Not just current
Itinerary | Edit destination order (drag) | Medium | v1.1
Itinerary | Day notes/mood | Low | v1.2
Budget | Advanced expense settlement | High | v1.1 | Per-person detailed view
Budget | Budget categories custom | Low | v1.2
Journal | AI Travel Story | High | v2.0 | Full trip narrative
Journal | Travel Book themes | Medium | v1.1 | Multiple PDF themes
Journal | Memory of the Day push notification | High | v1.1
Explore | GPS nearby suggestions | High | v1.2 | Needs Places API
Explore | Open Now filter | Medium | v1.2
Import | PDF booking import | High | v1.1 | Premium
Import | Flight import | High | v1.1 | Premium
Import | Booking.com / Airbnb import | High | v1.1 | Premium
Import | Gmail email parsing | Medium | v2.0 | Premium
Import | Travel Inbox | Medium | v2.0 | Detects trip emails
Packing | Smart suggestions by destination | Medium | v1.1 | Thailand → sunscreen etc
Packing | Predefined templates | Medium | v1.1 | Beach, Camping, Business
Offline | Offline mode (itinerary + docs) | High | v1.2 | Critical for international travel
Widget | Android home screen widget | Medium | v2.0 | Today's activities
Social | Group activity feed | High | v1.1 | Who added what
Social | Comments on activities | Low | v2.0
AI | AI itinerary optimization | High | v2.0 | Premium
AI | Smart reminders (context-aware) | High | v1.1
Monetization | Premium subscription (Stripe) | Critical | v1.1 | Post-launch
Maps | Real map with pins | High | v1.2 | Google Maps integration